## F2
SEVERITY
Risk | Result | Response | Likelihood | Impact | Risk Level | Date of RS | Revisited |  |  | Minimal | Minor | Moderate | Major | Severe
Loss of data | Likelihood and implications of data loss | Data replication | Likely | Minor | 6 | 2021-06-07 | 2021-06-13 | LIKELIHOOD | Guaranteed | 5 | 10 | 15 | 20 | 25
Recurring or prolonged interruptions of IT services supporting processes | Unable to run the app | Resilience and disater recovery plans in place | Likely | Severe | 15 | 2021-06-07 | 2021-06-13 |  | Expected | 4 | 8 | 12 | 16 | 20
Accidental human interference | Accidentally deleting files | Configure permissions properly and back up regularly | Likely | Major | 12 | 2021-06-07 | 2021-06-13 |  | Likely | 3 | 6 | 9 | 12 | 15
DDOS Attack | Causes a denial of service for users, i.e. unabvle to log in the app | Configure the firewall properly and have good DDOS mitigation | Possible | Severe | 10 | 2021-06-07 | 2021-06-13 |  | Possible | 2 | 4 | 6 | 8 | 10
Users forget passwords | User won't be able to login | Recover your password options | Guaranteed | Minimal | 5 | 2021-06-07 | 2021-06-13 |  | Unlikely | 1 | 2 | 3 | 4 | 5
Data leakage/theft | Access to database | Access to database managed by multifactor authentication | Possible | Severe | 10 | 2021-06-08 | 2021-06-13
User passwords can be guessed or cracked | Hacker will have access to user's information | Password policy in place(must have letters, numbers and symbols…) | Possible | Minor | 4 | 2021-06-11 | 2021-06-13
Data/Information Sabotage | Data will be exposed | Data Encryption: Make sure app connects to web services using secure connection protocols such as HTTPS. | Possible | Moderate | 6 | 2021-06-11 | 2021-06-13
Apps new features released | Denied access to Repo from Git Bash | Re-install or update the app | Likely | Moderate | 9 | 2021-06-11 | 2021-06-13